WOODLAND REMOVAL                                        LIFE09NAT/IE/000222 :January 2016.

| LIFE Project Site no. | SITE NAME | Woodland Area(ha) | C1-chainsaw (Ha) | C2-Machine(ha) | Windrow or Brash mat | Commercial Felling (ha) | Unplanted Areas (ha) | Restoration area (ha) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Curraghlehanagh Bog SAC 002350 | 11.08 | nil | nil | Brash mat | 11.08 | nil | 11.08 |
| 2 | Monivea SAC 002352 | 8.65 | nil | nil | BOTH W=1.5ha | 8.65 | nil | 8.65 |
| 3 | Lough Ree SAC000440 Kilteevan=11.88 Tonagh=22.49 Muckanagh=10.07 | 11.88 22.49 10.07 | nil 1.0 nil | nil 0.5 nil | W=3ha n/a Brash mat | 11.88 Nil 10.07 | nil 20.99ha nil | 11.88 22.49 10.07 |
| 4 | Lough Forbes Complex SAC 001818 | 16.17 | nil | 4.3 | C2 and Brash mat | 10.81 | 1.06 | 16.17 |
| 5 | MoneyBeg & Clareisland Bogs SAC 002340 | 14.16 | nil | nil | Brash mat | 14.16 | nil | 14.16 |
| 6 | Derrinlough Bog NHA 001254 | 58.81 | 1.2 | nil | Brash mat W=3ha | 57.61 | nil | 58.81 |
| 7 | Keeloges Bog NHA 000281 | 4.21 | 1.65 | nil | Windrow 3ha | 2.56 | nil | 4.21 |
| 8 | Ballygar Bog NHA 000229 | 28.41 | nil | nil | Brash mat W=8ha | 27.01 | 1.4 | 28.41 |
| 9 | Aughrim Bog NHA 001227 | 109.45 | nil | nil | BOTH W=36.22ha | 36.8 | 72.65 | 109.45 |
| 10 | L.ough Kinale & Derragh Lough NHA 000985 | 36.67 | 1.0 | nil | n/a | nil | 35.67 | 36.67 |
| 11 | Mount Jessop bog NHA 001450 | 71.17 | 42.0 | 3.0 | C2 and Brash mat | 19.37 | 6.8 | 71.17 |
| 12 | Girley Bog NHA 001580 | 33.08 | 4.0 | 3.2 | Windrow 25ha | 25.88 | nil | 33.08 |
| 13 | Lough Derravaragh NHA 000684 | 22.31 | 1.0 | nil | Windrow 3ha | 21.31 | nil | 22.31 |
| 14 | Wood down Bog NHA 000694 | 50.55 | nil | 2.0 | Windrow 42.04ha | 40.05 | 8.5 | 50.55 |
| 15 | Scohaboy Bog NHA 000937 | 72.06 | 9.5 | 5.0 | BOTH W=3ha | 14.5 | 43.06 | 72.06 |
| 16 | Arragh More Bog NHA 000640 | 90.83 | 81.08 * | nil | W=1.5 | Nil ** | 12.01 | 90.83*** |
| 17 | Cangort Bog NHA 000890 | 13.22 | nil | 6.5 | C2 and Brash mat | 6.4 | 0.32 | 13.22 |
|  | TOTAL | 685.27 | 142.43 | 24.5 | 129.26 | 318.14 | 202.46 | 685.27 |

TECHNICAL ISSUES

2. Reporting of Actions

General:

Raised bog restoration on afforested sites often presents unique challenges. Plantations are often difficult to access. Therefore it is difficult to measure or predict precisely exact areas for commercial felling, fell to waste by chainsaw or machine. Commercial felling proved possible on sites where it was not thought possible at the outset. Therefore the table above details where C1 actions were partially or completely unnecessary due to commercial felling. Sites numbers 11 and 12 have a larger area than anticipated in C1.Site 12 has a marginal difference as this was calculated when completed using GPS technology. Site 11 at Mount Jessop was too wet for Machinery and we used C1 there.

Movement between actions C1 and C2

There was substantive movement between actions C1 and C2 at sites 11 and 16.

Site 11 was particularly wet and dangerous for machine work during proposed operations.C1 was the only feasible option.

Site 16 proved more suitable to C1 due to erratic bog holes and swamps.

C1-Planned=157.25ha.Actual=142.43.Variance=14.82ha or 91% completed.re. table above.

C2- Planned=87.1ha.   Actual=24.5ha Variance=  62.6ha  or 28% completed.re Table above. Site 16 Planned for 50ha though nil completed. Work proved more suitable and cheaper  to be undertaken under C1.

C3-Planned =379.67.Actual=129.26ha.Variance= 250.41ha or 34% completed.Re.Table above. We can confirm that all sites are cleared to the standard expected.Brashmats or Extraction racks are the branches and waste material layed on the ground under the timber harvester to provide access and stability.W denotes windrow in Table.

Detailed calculation of individual site areas measured using GIS technology by Fernando Fernandez from  NPWS in 2015.This is a more accurate measurement and will show slight variation from original areas on some sites. Original areas calculated in 2009.

*Site 16-ArraghMore bog: Site originally listed as 100.68 ha. This was in error and became evident with GIS mapping.

**Site commercially felled in 2004/2005 season. Regrowth of pine was extremely vigorous. As a consequence tree removed was classified as fell to waste by chainsaw .The work was completed under contract  at €700 per Hectare.

***This is the correct Area for the site. Control of invasives by action C1 took place over several years  and some areas were treated twice. Therefore  81.08ha plus 12.01 ha marginally exceeds final corrected area  90.83ha.

3.Additional work at Aughrim Bog NHA.

65ha has been added to the project at Site No. 9 Aughrim Bog.This  exhausted our External Assistance budget.Action C4 installation and Dam repair were operated primarily from our external assistance budget.